## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to AI Stock Signal & ETF Prediction Project | MUST HAVE | No Dependency | Tarun | 3- Completed
S1 | S1 | US-002 | Understanding Stock Market Basics, Signals & Project Scope | MUST HAVE | Online research | Tarun | 3- Completed
S2 | S2 | US-003 | Workflow Design & Architecture Planning for AI Dashboard | MUST HAVE | Figma | Tarun | 3- Completed
S2 | S2 | US-004 | Agile Documentation Setup (Sprint plan, stories, GitHub workflow) | MUST HAVE | Agile Template | Tarun | 3- Completed
S3 | S3 | US-005 | Environment Setup (Python, Virtual Env, Libraries, Repo Setup) | MUST HAVE | Python, VS Code | Tarun | 3- Completed
S3 | S3 | US-006 | Streamlit Dashboard Basic UI & Page Structure Creation | MUST HAVE | Streamlit | Tarun | 3- Completed
S4 | S4 | US-007 | Dashboard Integration with Sample Stock Data & Visualizations | MUST HAVE | Pandas, Plotly | Tarun | 3- Completed
S4 | S4 | US-008 | Coordination with ML & Backtesting Teams for Output Requirements | MUST HAVE | Team discussions | Tarun | 3- Completed
S5 | S5 | US-009 | Integration of ML Buy/Hold/Sell Signals into Dashboard | MUST HAVE | ML Team Output | Tarun | 3- Completed
S6 | S6 | US-010 | Backtesting Metrics Visualization (Equity Curve, Drawdown, Returns) | MUST HAVE | Backtesting Team Data | Tarun | 3- Completed
S7 | S7 | US-011 | Alerts & User Controls (Email / Popup Alerts Configuration) | MUST HAVE | Streamlit, SMTP | Tarun | 3- Completed
S8 | S8 | US-012 | Final Testing, UI Refinement & Deployment Preparation | MUST HAVE | Render / Cloud Platform | Tarun | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 22 | 17 | 14 | 8 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to AI Stock Signal & ETF Prediction Project | 2025-11-26 | 2025-12-02 | Tarun | Others | 3 – Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Stock Market Basics, Signals & Domain Understanding | 2025-12-03 | 2025-12-09 | Tarun | Research | 3 – Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Workflow Creation & High-Level Architecture Design | 2025-12-10 | 2025-12-16 | Tarun | Design | 3 – Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Agile Documentation Setup (Sprint, Stories, GitHub Flow) | 2025-12-17 | 2025-12-23 | Tarun | Others | 3 – Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-002 | 5 | Python Environment Setup & Library Installation | 2025-12-17 | 2025-12-23 | Tarun | Coding | 3 – Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 6 | Streamlit Dashboard Basic Layout & Navigation | 2025-12-24 | 2025-12-30 | Tarun | Build | 3 – Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-003 | 7 | Stock Data Integration & Chart Rendering | 2025-12-24 | 2025-12-30 | Tarun | Coding | 3 – Completed | 10 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-004 | 8 | ML Signal Integration (Buy / Hold / Sell) | 2025-12-31 | 2026-01-06 | Tarun | Integration | 3- Completed | 12 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 9 | Backtesting Metrics Visualization | 2026-01-07 | 2026-01-13 | Tarun | Analysis | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-005 | 10 | Alerts Configuration, Testing & Deployment | 2026-01-14 | 2026-01-21 | Tarun | System Test | 3- Completed | 8 | Day 1: 3; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 0
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Initial lack of clarity on overall AI Stock Signal project scope and expected outputs | Discussed project objectives with mentor and reviewed reference materials
Sprint 1 | Day 4 | Confusion about role-specific responsibilities between Dashboard, ML, and Backtesting teams | Conducted cross-team discussion to clearly define inputs and outputs
Sprint 2 | Day 6 | Difficulty understanding Agile story writing and MOSCOW prioritization | Reviewed Agile template and clarified doubts during mentor-led session
Sprint 2 | Day 8 | Uncertainty in designing dashboard workflow before final ML outputs | Created a flexible dashboard wireframe that supports dynamic ML data
Sprint 3 | Day 11 | Issues in setting up Streamlit environment and library compatibility | Reinstalled dependencies and validated setup using sample applications
Sprint 3 | Day 13 | Challenges in rendering interactive charts with stock data | Referred official documentation and tested multiple visualization libraries
Sprint 4 | Day 16 | Delay in receiving finalized data format from Backtesting team | Used mock JSON data to continue dashboard development
Sprint 5 | Day 22 | Difficulty integrating ML Buy/Hold/Sell signals with confidence scores | Coordinated with ML team to standardize signal output structure
Sprint 6 | Day 27 | Performance issues when loading multiple dashboard components | Optimized data loading and applied caching techniques in Streamlit
Sprint 7 | Day 31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback
Sprint 7 | Day 31 | Uncertainty around alert trigger conditions and notification flow | Designed configurable alert logic and validated with mentor feedback

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-26 | 2025-12-02 | Samruddhi Junavane,Polipalli Sai,Tarun,Shamrutha | Reviewing project documentation and understanding stock market basics | Assuming requirements without clarification | Participating in mentor and team discussions | Conducted requirement clarification session and aligned on project scope
2 | Sprint 2 | 2025-12-03 | 2025-12-09 | Tarun | Structuring Agile stories and sprint timelines | Writing vague or task-level stories | Following Agile methodology consistently | Refined user stories using MOSCOW prioritization
3 | Sprint 3 | 2025-12-10 | 2025-12-16 | Tarun,Polipalli Sai,Samruddhi Junavane,Shamrutha | Setting up Streamlit dashboard and Python environment | Delaying UI testing | Practicing incremental coding and testing | Successfully completed environment setup and basic dashboard layout
4 | Sprint 4 | 2025-12-17 | 2025-12-23 | Tarun,Samruddhi Junavane,Shamrutha | Integrating sample stock data and visualizations | Waiting for finalized ML outputs | Coordinating with ML and backtesting teams | Used mock data to complete dashboard visual components
5 | Sprint 5 | 2025-12-24 | 2025-12-30 | Tarun | Integrating ML Buy/Sell signals into dashboard | Hardcoding values in UI | Using dynamic and configurable data pipelines | Standardized ML signal format and integrated it into the dashboard
6 | Sprint 6 | 2025-12-31 | 2026-01-06 | Tarun,Shamrutha | Integrating alert functionality and trading notifications into the dashboard | Pushing changes without cross-team confirmation | Incremental testing after every integration | Resolved integration inconsistencies and stabilized dashboard features
7 | Sprint 7 | 2026-01-07 | 2026-01-13 | Tarun,Samruddhi Junavane,Shamrutha | Validating end-to-end data flow across all dashboard features | Ignoring minor UI inconsistencies | Peer reviews and team feedback sessions | Finalized feature set and prepared the system for demo and documentation
8 | Sprint 8 | 2026-01-14 | 2026-01-28 | Shamrutha,Samruddhi Junavane,Pollipalli Sai | Demo Video,Documentation,PPT | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission